## Trigger, Campaign & Deals Modul
Project Name: Pluto Project Link: https://crm.meetpluto.io/ SQA Engineer: Abdulla Al Bayzed Module: Trigger, Campaign & Deals, Subscription, Billing
Issue List for Pluto CRM
Date | Issue No | Issue Type | Status | Severity | Error Type | Module | Title | Description | Enviornment | Actual Result | Expected Result | Attachment | Remarks(Dev) | Remarks(SQA)
14/05/2025 | 1 | Bug | Fixed | Major | Functional | Campaign (Text) | Cannot save campaign text module when image is attached | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Text action 4. Type any content into the text box 5. Attach an image file using the attachment option 6. Click the Save button 7. Pay attention to the system response | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Cannot save campaign text module when image is attached | Campaign text module shoud be save with image | Attachment Link | Done | Done
14/05/2025 | 2 | Bug | Fixed | Major | Functional | Campaign (Email) | Email module in campaign fails to preview uploaded documents file | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the email option 4. Type any content into the text box 5. Attach any file (like: doc, txt, xl) 6. Click the Save button & go to the preview in deals 7. Pay Attention to the preview list | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Email module in campaign fails to preview uploaded documents file | Uploaded file must be shown in preview | Attachment Video | Done | Done
14/05/2025 | 3 | Bug | Fixed | Minor | GUI | Campaign (Email) | In campaign email module text highlight/background color overlap in email body preview when text font size 32 or over | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the email option 4. Type any content into the text box, increase text size & add color in the background 5. Click the Save button & go to the preview in deals 6. Pay Attention to the email body text background colour | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In campaign email module text highlight/background color overlap in email body preview when text font size 32 or over | Text highlight/background color should not be overlap in email body | Attachment Link | Done | Done
14/05/2025 | 4 | Bug | Unresolved | Minor | GUI | Campaign (edit & save) | In campaign does not shown any notification when edit & save the action | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign & edit any action 4. Click save button 5. Pay attention to the page | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In campaign does not shown any notification when edit & save the action | Notification should be shown when edit & save a campaign action | Attachment Link | Open | Open
15/05/2025 | 5 | Bug | Fixed | Minor | GUI | Campaign (Direct Mail) | In direct mail letter text format not same as letter card when save the letter action | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Direct mail 4. Select Letter option & select a template 5. Click save button then write something like letter and click generate 6. Click save button & select a date, time 7. Click save & Go to the campaign list and pay attention to the text format | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In direct mail letter text format not same as letter card when save the letter action | Letter text format should be same as letter card format | Attachment Link | Done | Done
15/05/2025 | 6 | Bug | Fixed | Major | Functional | Campaign (Direct Mail) | Custom Time Range (10:00 AM to 10:45 AM) Not Working in Direct Mail Letter Scheduling | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Direct mail 4. Select Letter option & select a template 5. Click save button then write something like letter and click generate 6. Click save button 7. Select a date & time(10:00am to 10:45am) & Click save 8. Pay Attention to the page | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Custom Time Range (10:00 AM to 10:45 AM) Not Working in Direct Mail Letter Scheduling | The Custom Time feature should work correctly for all valid time ranges | Attachment Link | Done | Done
15/05/2025 | 7 | Bug | Unresolved | Major | Functional | Direct Mail Voicemail Video Email Action Activity | Scheduled Time Not Displayed When Editing some action | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Direct mail 4. Select Letter option & select a template 5. Click save button then write something like letter and click generate 6. Click save button & Select a date-time 7. Click Save & Go to the edit option 8. Pay Attention to the time section | Operating System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Scheduled Time Not Displayed When Editing some action | Previously set scheduled time should be visible when editing the any action | Attachment Link | Open | Open
18/05/2025 | 8 | Enhancement | Unresolved | Average | Functional | Campaign (call bridge) | In save button not showing the loading indicator when save any action | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing or create new campaign module 4. Click on call bridge & fill up the required data 5. Click save or close button 6. Pay attention to the save & close load time | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In save button not showing the loading indicator when save any action | Loading Indicator should be shown for save action | Attachment video Link | Open | Open
18/05/2025 | 9 | Bug | Fixed | Minor | GUI | Deals(delete) | In Deals does not shown any notification when delete a deal | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Deals 3. Select a deal & delete it 4. Pay attention to the page | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In Deals does not shown any notification when delete a deal | Deleted notification must be shown when delete a deals | Attachment Link | Done | Done
18/05/2025 | 10 | Bug | Unresolved | Major | Functional | Deals(Move) | Deals not moving to another pipeline before deletion | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Deals 3. Select a deal & click delete button 4. Click Yes button and select pipeline & stage 5. Pay attention to the pipeline where transfer the deals | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Deals not moving to another pipeline before deletion | Deals should be move to the another pipeline before deletion | Attachment Link | Open | Open
18/05/2025 | 11 | Bug | Unresolved | Minor | GUI | Campaign (Custom date) | In campaign custom date not shown the calendar icon when select the custom date | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the( text, email, video email, voice mail) 4. Input the required data and click custom date 5. Pay attention to the custom date format | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In campaign custom date not shown the calender icon when select the custom date | Calender format should be shown in custom date | Attachment Issue picture | Open | Open
19/05/2025 | 12 | Bug | Unresolved | Minor | GUI | Campaign | In campaign(email, voicemail, call bridge) not show notification when save it | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select email, voicemail or call bridge 4. Input the required data in the field & click save button 5. Pay attention to the page no notification show | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In campaign(emai, voicemail, call bridge) not show notification when save it | Notification should be shown when save any campaign settings | Attachment Video | Open | Open
19/05/2025 | 13 | Enhancement | Unresolved | Average | Functional | Campaign (Text) | Attach File’ Option in Campaign Text Settings Only Supports Images | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open Text & Input required field data 4. Click attach file button & try to attach any types of file 5. Pay attention to the attach file only image can add | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Attach File’ Option in Campaign Text Settings Only Supports Images | All type of documents should be attach in text settings attach file [Or change the attach file name to Attach image/Attachment] | Attachment Video link | Open | Open
19/05/2025 | 14 | Bug | Unresolved | Minor | GUI | Campaign (Voicemail) | Voicemail Without Title Sends Successfully But No Notification Is Displayed | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open voice mail & upload a voice recording or create 4. No title set for it & click the save button 5. Pay attention to the settings | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Voicemail Without Title Sends Successfully But No Notification Is Displayed | Notification should be shown when not set any title | Attachment Link | Open | Open
19/05/2025 | 15 | Bug | Unresolved | Average | Functional | Campaign (action & activity) | In save button not showing the loading indicator when save any module | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing or create new campaign module 4. Click on action or activity option & fill up the required data 5. Click save or close button 6. Pay attention to the save & close load time | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In save button not showing the loading indicator when save any module | Loading Indicator should be shown for save actions | Attachment video link | Open | Open
19/05/2025 | 16 | Bug | Unresolved | Major | Functional | Campaign (Text) | Image Not Saved After Removing and Reattaching in Campaign Text Module Edit Mode | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Text action 4. Type any content into the text box & attached an image 5. Click save button & also click edit button 6. Remove the picture & click save 7. Again click edit button attach an image again & click save button 8. Pay attention to the saving | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Image Not Saved After Removing and Reattaching in Campaign Text Module Edit Mode | Reattached image should be saved successfully after editing | Attachment Link | Open | Open
20/05/2025 | 17 | Bug | Unresolved | Minor | GUI | Campaign (Text) | Campaign Text Action Allows Only Image Attachment but Displays "Send an MMS with Image/Audio/PDF" | Steps to Reproduce: Open https://crm.meetpluto.io/ Navigate to Marketing → Campaigns Open any existing campaign and select the Text action Type any content into the text box & attached an image Click save button Pay attention to the preview | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Campaign Text Action Allows Only Image Attachment but Displays "Send an MMS with Image/Audio/PDF" | Attachment info should accurately reflect supported file types (e.g., only image) | Attachment Link | Open | Open
20/05/2025 | 18 | Bug | Unresolved | Minor | GUI | Campaign (Email) | GIF in Campaign Email Body Breaks Text Formatting and Displays Last Text Under the GIF in Preview | Steps to Reproduce: Open https://crm.meetpluto.io/ Navigate to Marketing → Campaigns Open any existing campaign and select the Email action Type any content into the text box with more text & attached a Giphy Click save button Pay attention to the deals preview option | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | GIF in Campaign Email Body Breaks Text Formatting and Displays Last Text Under the GIF in Preview | Text should display correctly and not shift under the GIF in preview | Attachment Link | Open | Open
20/05/2025 | 19 | Bug | Unresolved | Major | Functional | Campaign (Action) | Campaign Action Not Saving Changes After Second Edit | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select the Action 4. Input required field & Click save button 5. Now click in edit button edited the action & save it 6. Again click edit button and edited the action & click save button 7. Pay attention to the saving | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | Campaign Action Not Saving Changes After Second Edit | Action changes should be saved successfully every time after editing | Attachment Link | Open | Open
21/05/2025 | 20 | Bug | Unresolved | Minor | GUI | Campaign (Activity) | In campaign(activity) module time show calendar icon instead of clock icon | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Marketing → Campaigns 3. Open any existing campaign and select 3 dot button 4. Click Activity 5. Pay attention to the time place | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In campaign(activity) module time show calendar icon instead of clock icon | Clock icon should be shown in time place | Attachment Link | Open | Open
21/05/2025 | 21 | Bug | Fixed | Average | Functional | Calendar (Appointment Schedule) | In Calendar(Apointment Schedule) cancel button not work when click on it | Steps to Reproduce: 1. Open https://crm.meetpluto.io/ 2. Navigate to Calendar → Appointment Schedule 3. Open any Online Appointment Scheduling 4. Click the cancel button 5. Pay attention to the working of cancel button | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit) | In Calendar(Apointment Schedule) cancel button not work when click on it | Cancel button should be work | Attachment Link | Done | Done
25/05/2025 | 22 | Bug | Fixed | Average | Functional | Billing dashboard (Payment) | In billing dashboard duplicate payment entries displayed when clicking "current history" button | Steps to Reproduce: 1. Log into https://insurance-billing.pypepro.com/billing 2. Click on payments option 3. Click archive & current history 2/3 times 4. Pay attention to the current history | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In billing dashboard duplicate payment entries displayed when clicking "current history" button | Clicking "Current History" should display each payment only once, with no duplicates. | Attachment Link | Done | Done
26/05/2025 | 23 | Bug | Unresolved | Average | Functional | Billing dashboard (Auto recharge) | Auto Recharge" Button Temporarily Disappears When Navigating Between Page | Steps to Reproduce: 1. Log into https://insurance-billing.pypepro.com/billing 2. Select auto-recharge required field & Click save change 3. Go to the new pages or any other option & again click on the subscription 4. Pay attention to the auto-recharge button | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Auto Recharge" Button Temporarily Disappears When Navigating Between Page | The "Auto Recharge" button should remain consistently visible across all relevant pages | Attachment Link | Open | Open
26/05/2025 | 24 | Bug | Unresolved | Average | Functional | Billing dashboard (Save Change) | Save Changes" Button Reappears After Click and Disappears on Page Change | Steps to Reproduce: 1. Log into https://insurance-billing.pypepro.com/billing 2. Click on payments option 3. Click archive & current history 2/3 times 4. Pay attention to the current history | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Save Changes" Button Reappears After Click and Disappears on Page Change | Auto Recharge button flickers on page change – should stay visible consistently | Attachment Link | Open | Open
26/05/2025 | 25 | Bug | Unresolved | Minor | GUI | Billing dashboard (Payment method) | In payment method no notification displayed when deleting or setting a default card | Steps to Reproduce: 1. Log into https://insurance-billing.pypepro.com/billing 2. Go to subscription option and click payment method 3. Click pen button and delete a card or set a card as default from this 4. Pay attention to the page | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In payment method no notification displayed when deleting or setting a default card | A confirmation notification should appear after successfully deleting or adding a card as default | Attachment Link | Open | Open
26/05/2025 | 26 | Bug | Unresolved | Major | Functional | Subscription (Payment system) | In Subscription Unable to Set Valid Card as Primary After Initial Declined Card | Steps to Reproduce: 1. Create account in https://insurance-billing.pypepro.com/trial/get-started with decline card 2. Make payment for the 1st renew package using simulator advance time 3. Now log in into https://insurance-billing.pypepro.com/ 4. Add new valid card and make it primary card 5. Now pay attention to the making primary card | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | In Subscription Unable to Set Valid Card as Primary After Initial Declined Card | User can set a newly added valid card as primary after initial card is declined | Attachment Link | Open | Open
26/05/2025 | 27 | Bug | Unresolved | Major | Functional | Subscription date | Next Billing Cycle Starts from Trial End Date Even When Payment Is Delayed | Steps to Reproduce: 1. Create account in https://insurance-billing.pypepro.com/trial/get-started with valid card 2. Make payment for the 1st renew package not due date using simulator advance time 3. Now pay attention to the next billing date | Operation System: Windows 11 Browser: Google Chrome: Version 136.0.7103.114(official Build) (64-bit) Brave: Version 1.78.102 Chromium: 136.0.7103.113 (Official Build) (64-bit)" | Next Billing Cycle Starts from Trial End Date Even When Payment Is Delayed | Billing cycle should start from the actual payment date, not the trial end date, if payment is delayed | Attachment Link | Open | Open